# ThaiHealth (สสส.) – Draft Proposal: Community Oral Cancer Risk Reduction and Volunteer Capacity Building in Health Region 10

Why ThaiHealth: ThaiHealth funds health promotion and prevention, not AI development. This proposal funds the volunteer training, community awareness and risk-factor reduction (betel quid, tobacco, alcohol) around the pilot. The app is a tool within that work.

Applicant: a Thai organisation: hospital, Mahidol University, community organisation or foundation [CONFIRM eligible applicant types and the open-grant channel at thaihealth.or.th]

Language: Thai

## ชื่อโครงการ

TH: โครงการพัฒนาศักยภาพ อสม. และชุมชนในการลดปัจจัยเสี่ยงและคัดกรองมะเร็งช่องปากด้วยเทคโนโลยีดิจิทัล เขตสุขภาพที่ 10

EN: Building volunteer and community capacity to reduce risk factors and screen for oral cancer with digital tools, Health Region 10

## หลักการและเหตุผล (Rationale)

Betel quid, tobacco and alcohol use in the northeast [FILL: local data]

Oral cancer is often found late; volunteers have about one day of training and paper forms

Opportunity: train volunteers to (1) give brief advice on quitting betel, tobacco and alcohol; (2) screen with a simple app; (3) follow up referrals

## วัตถุประสงค์ (Objectives)

1. Train 20 lead volunteer trainers and ~300 volunteers in oral cancer risk communication, brief cessation advice and app-based screening

2. Screen [FILL: N] adults aged 40+ in [FILL: N] sub-districts, and refer and follow up all high-risk people

3. Deliver community campaigns on betel quid, tobacco and alcohol in [FILL] villages

4. Link people who want to quit to cessation services (e.g. the Thai national quitline 1600 [CONFIRM] and local clinics)

## กลุ่มเป้าหมายและพื้นที่ (Target group & area)

[FILL: provinces, districts, sub-districts; population aged 40+]

## กิจกรรม (Activities)

| Activity | Month |
| --- | --- |
| Lead-trainer workshop; picture-based manual (Thai/local language) | 1–2 |
| Cascade training of volunteers | 2–4 |
| Community campaigns (village broadcasts, posters, LINE OA, temple and market events) | 3–10 |
| Screening days + home visits | 4–10 |
| Referral follow-up and cessation linkage | 4–12 |
| Community feedback and evaluation | 11–12 |

## ตัวชี้วัด (Indicators)

| Indicator | Target |
| --- | --- |
| Volunteers trained | 300 |
| Adults screened | [FILL] |
| High-risk people referred who attended | ≥ [FILL]% |
| People given brief cessation advice | [FILL] |
| People attempting to quit betel/tobacco/alcohol | [FILL] |
| Women in lead-trainer roles | ≥ [FILL]% |

## ความยั่งยืน (Sustainability)

Embed training in the district volunteer programme; co-financing from the sub-district health fund (กองทุนหลักประกันสุขภาพระดับท้องถิ่น/ตำบล); Provincial Health Office support.

## งบประมาณ (Budget) [FILL; use ThaiHealth categories]

Training costs; volunteer compensation; communication materials; screening-day logistics; referral transport support; monitoring and evaluation; administration.

## Partners

Hospitals [FILL]; Provincial Health Offices; sub-district administrative organisations (อบต.); district volunteer clubs; Mahidol University; KPD (app and training game, provided in-kind).