# Grant Application Templates – AI Early Oral Cancer Detection (Thailand)

Prepared 12 Oct 2026. One template per funder, numbered in the same order as the "most likely to work" ranking.

## How to use these templates

1. Fill in `01_Common_Information_Pack` first. About 70% of what every funder asks for is the same: team, hospitals, problem, aims, methods, budget, ethics. Each grant template points back to the section of the Common Pack to copy from ("→ CP §4").

2. Then open the template for the grant you are applying to. Each one contains:

Eligibility check – confirm you can apply before doing any work

Registrations & approvals – things that take weeks, so start them first

Document checklist – every file to submit, with page limits

Section-by-section fill-in template – what each section must say

Budget template – the categories that funder uses

Scoring tips

Verify before submitting – items that change from call to call

3. Always download the official call document (the NOFO, ประกาศ, or call for proposals) for the cycle you apply to. Page limits, deadlines and forms change every year. Anything marked [CONFIRM] is something you must check in the official call.

## Start these NOW (they take the longest)

| Task | Needed for | Typical time |
| --- | --- | --- |
| Register every investigator in NRIIS (nriis.go.th) | All Thai funders (#1–4, #14 Thai side) | 1–2 weeks |
| Ethics committee (IRB/EC) approval at each of the 4 hospitals, or one central approval accepted by all | All funders that involve patients | 1–3 months |
| Data-sharing agreement between the 4 hospitals (Thai PDPA compliant) | All funders | 1–3 months |
| Institution registers for a UEI in SAM.gov (foreign entities also need an NCAGE code) | All NIH grants (#9–13, #17–18) | 4–8 weeks |
| Grants.gov and eRA Commons institutional accounts plus a PI account | All NIH grants | 2–4 weeks after SAM |
| ORCID iD for every key person, linked to eRA Commons and SciENcv | All NIH grants (Common Forms biosketch) | 1 day |
| Federalwide Assurance (FWA) for each hospital's ethics committee (OHRP) | NIH, before award | 2–6 weeks |
| Start collecting a pilot image dataset and baseline AI accuracy results | Makes every application much stronger | ongoing |

## File index

| # | File | Funder |
| --- | --- | --- |
| 00 | START_HERE | This guide |
| 01 | Common_Information_Pack | Fill this first |
| 02 | NRCT | National Research Council of Thailand |
| 03 | HSRI | Health Systems Research Institute (สวรส.) |
| 04 | PMU-C_PMU-B | Program Management Units (บพข. / บพค.) |
| 05 | TSRI_Fundamental_Fund | TSRI Fundamental Fund (via institution) |
| 06 | Compute_Credits | NVIDIA / AWS / Microsoft |
| 07 | ThaiHealth | Thai Health Promotion Foundation (สสส.) |
| 08 | UICC | UICC fellowships & grants |
| 09 | NCI_Thailand | National Cancer Institute Thailand / DMS (partnership) |
| 10 | NIH_PA-25-253_R21 | NIH Exploratory Grants in Cancer Control ⭐ |
| 11 | NIH_IMAT_R61 | NIH Early-Stage Technology Development (RFA-CA-27-001 / 28-001) |
| 12 | NIH_IMAT_R33 | NIH Advanced Technology Validation (RFA-CA-27-002 / 28-002) |
| 13 | NIH_ITCR_U01 | NIH Informatics Technologies (RFA-CA-27-019) |
| 14 | NIH_Secondary_Data_R21_R01 | NIH Secondary Analysis of Existing Data (PAR-25-096 / 095) |
| 15 | e-ASIA_JRP | e-ASIA Joint Research Program |
| 16 | IARC | IARC collaboration / fellowships |
| 17 | Wellcome | Wellcome Trust |
| 18 | NIH_PAR-25-167_R01 | NIH Cancer Prevention & Control Clinical Trials |
| 19 | NIH_PAR-25-081_R01 | NIH Early-Phase Clinical Trials (Diagnosis) |
| 20 | Gates_Google | Gates Grand Challenges / Google.org |
| 21 | AMED_KHIDI | Japan AMED / Korea KHIDI |
| 22 | Pfizer_Industry | Pfizer Global Medical Grants / industry |

## Important rule changes (2025–2026) that affect you

NIH foreign partners: NIH no longer funds foreign partners through ordinary subawards. For due dates on or after 25 Jan 2026, applications that request money for foreign components must use NIH's new linked-award structure (PF5/UF5 activity codes, each foreign institution as its own "International Project Component"). If a US university leads and your Thai hospitals are partners, this applies to you. If a Thai hospital is the applicant itself, ask the NIH program officer how the other three Thai hospitals should be included. (NOT-OD-25-104, NOT-OD-25-155)

NIH Common Forms: Since 25 Jan 2026, biosketches and Current & Pending (Other) Support must be made in SciENcv, and every key person must link their ORCID and eRA Commons accounts. (NOT-OD-26-018)

NIH and AI-written applications: NIH does not treat applications "substantially developed by AI" as original, and limits each PI to 6 applications per calendar year. Write the science yourselves. (NOT-OD-25-132)

NVIDIA Academic Grant Program: not accepting applications as of Oct 2026. Watch for the next call.

Thai funders: almost all submissions go through NRIIS, in Thai, and are certified by your institution's research office before the funder's deadline. The institution's internal deadline is usually 1–2 weeks earlier than the funder's.