# Common Information Pack – fill in once, reuse everywhere

Every grant template refers back to these sections ("→ CP §3"). Keep an English and a Thai version of the key sections: Thai funders require Thai in NRIIS, and international funders require English.

## §1 Project identity

| Field | English | Thai (ภาษาไทย) |
| --- | --- | --- |
| Project title (≤ 200 characters) | ____________________ | ชื่อโครงการ: ____________________ |
| Short title / acronym | ____________________ |  |
| Keywords (5–8) | oral cancer; early detection; artificial intelligence; deep learning; screening; oral potentially malignant disorders; Thailand; ____ | คำสำคัญ: ____ |
| Duration (months) | ____ | ระยะเวลา: ____ เดือน |
| Start date (planned) | ____ |  |
| Total budget requested (THB / USD) | ____ | งบประมาณรวม: ____ บาท |
| Technology Readiness Level (TRL) now → at end | TRL __ → TRL __ | ระดับความพร้อมเทคโนโลยี |
| Societal Readiness Level (SRL) now → at end | SRL __ → SRL __ | ระดับความพร้อมสังคม |

One-sentence summary (≤ 40 words):

____________________________________________

Elevator pitch (≤ 150 words): the problem, what you will build, how you will test it, and who benefits.

____________________________________________

## §2 Lead institution & partner hospitals

|  | Lead (applicant) | Partner 2 | Partner 3 | Partner 4 |
| --- | --- | --- | --- | --- |
| Hospital name (EN) | Huathahan Hospital (confirm official name) | ______ | ______ | ______ |
| Hospital name (TH) | ______ | ______ | ______ | ______ |
| Type (university / military / MOPH provincial / private) | ______ | ______ | ______ | ______ |
| Province / region | ______ | ______ | ______ | ______ |
| Legal address | ______ | ______ | ______ | ______ |
| Site lead (name, position, department) | ______ | ______ | ______ | ______ |
| Research office contact (name, email) | ______ | ______ | ______ | ______ |
| Ethics committee name + FWA no. (if any) | ______ | ______ | ______ | ______ |
| Tax ID / registration no. | ______ | ______ | ______ | ______ |
| UEI (SAM.gov) – NIH only | ______ | ______ | ______ | ______ |
| Annual oral/head & neck cancer patients seen | ______ | ______ | ______ | ______ |
| Annual dental/oral clinic visits | ______ | ______ | ______ | ______ |
| Existing oral images available (number, type) | ______ | ______ | ______ | ______ |
| Biopsy/histopathology capacity (yes/no, turnaround) | ______ | ______ | ______ | ______ |
| Catchment population / referral network | ______ | ______ | ______ | ______ |
| Role in project | ______ | ______ | ______ | ______ |

Why these 4 hospitals together? Geographic and population diversity, referral pathways, and complementary strengths.

____________________________________________

Other partners (university AI lab, NECTEC, foreign collaborator, industry):

| Partner | Country | Role | Contact | Letter of support? |
| --- | --- | --- | --- | --- |
| ______ | ______ | ______ | ______ | ☐ |

## §3 Team (one row per person; keep a CV for each)

| Name (EN/TH) | Title, degree | Institution | Project role | % effort / months per year | Key expertise | ORCID | eRA Commons ID | NRIIS registered |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ______ | ______ | ______ | Principal Investigator | ______ | ______ | ______ | ______ | ☐ |
| ______ | ______ | ______ | Co-I (oral & maxillofacial surgery / oral medicine) |  |  |  |  | ☐ |
| ______ | ______ | ______ | Co-I (oral pathology) |  |  |  |  | ☐ |
| ______ | ______ | ______ | Co-I (AI / computer science) |  |  |  |  | ☐ |
| ______ | ______ | ______ | Co-I (biostatistics / epidemiology) |  |  |  |  | ☐ |
| ______ | ______ | ______ | Co-I (public health / health economics) |  |  |  |  | ☐ |
| ______ | ______ | ______ | Project coordinator |  |  |  |  | ☐ |

Gaps funders will notice: pathology (the gold standard for labels), biostatistics, AI engineering, health economics. Fill all four.

For each person, keep up to date:

☐ CV in English (2–5 pages)

☐ CV in Thai (ประวัติคณะผู้วิจัย, NRIIS format)

☐ NIH Common Form biosketch made in SciENcv (NIH only)

☐ Last 5 years of publications, grants held, and awards

☐ Current & pending support (other grants, with % effort)

## §4 Problem & significance (with references)

Use the most recent figures and cite each one (GLOBOCAN, Thai Cancer Registry, NCI Thailand).

| Fact | Value | Source |
| --- | --- | --- |
| Oral cavity & lip cancer new cases per year, Thailand | ______ | GLOBOCAN 20__ |
| Deaths per year, Thailand | ______ |  |
| % diagnosed at late stage (III–IV) in Thailand / at your hospitals | ______ |  |
| 5-year survival: early stage vs late stage | ______ vs ______ |  |
| Main risk factors in your population (tobacco, alcohol, betel quid, HPV) | ______ |  |
| Ratio of oral specialists to population in your provinces | ______ |  |
| Current screening practice in Thailand (who screens, how) | ______ |  |
| Cost of late-stage treatment vs early treatment (THB) | ______ |  |

Problem statement (½ page):

____________________________________________

Gap: why current methods (visual exam by non-specialists, referral delays) miss early cancer.

____________________________________________

Why AI, why now: smartphone cameras, published AI accuracy for oral lesions, Thai digital health policy.

____________________________________________

## §5 Aims / objectives

Keep to 2–4 aims. Each must be measurable.

| Aim | What you will do | How success is measured | Months |
| --- | --- | --- | --- |
| 1. Build dataset | Collect ____ standardised oral images with histopathology-confirmed labels from 4 hospitals | ____ images; inter-rater kappa ≥ ____ | 1–__ |
| 2. Develop AI model | Train/validate a model to classify normal / OPMD / cancer | Sensitivity ≥ __%, specificity ≥ __%, AUC ≥ __ on external hospital | __–__ |
| 3. Clinical validation | Prospective test in ____ participants at ____ sites, vs specialist exam + biopsy | Diagnostic accuracy; time to referral | __–__ |
| 4. Implementation | Pilot use by ____ (dentists / village health volunteers / primary care) | Uptake, usability (SUS score), cost per case detected | __–__ |

## §6 Methods (reuse the text across applications)

6.1 Study design: retrospective + prospective, multi-centre diagnostic accuracy study

____________________________________________

6.2 Participants: inclusion/exclusion criteria, sample size and its calculation, recruitment at each site

| Site | Retrospective images | Prospective participants | Expected positives |
| --- | --- | --- | --- |
| ______ | ______ | ______ | ______ |

6.3 Image acquisition: device (smartphone model / intraoral camera), standard protocol, number of views per patient, who takes the photos

____________________________________________

6.4 Reference standard / labelling: histopathology, expert panel, number of annotators, adjudication

____________________________________________

6.5 AI approach: architecture, training/validation/test split by hospital (external validation), handling of class imbalance, explainability (heatmaps), bias checks by sex, age, skin tone and site

____________________________________________

6.6 Statistics: sensitivity, specificity, AUC with 95% CI, comparison with general dentists and non-specialists, STARD / TRIPOD+AI / CONSORT-AI reporting

____________________________________________

6.7 Implementation & health economics: workflow, training, referral pathway, cost-effectiveness model

____________________________________________

6.8 Risks & mitigation

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Too few cancer cases |  | Retrospective archives; extend recruitment; add sites |
| Image quality varies by site |  | Standard protocol; quality-check app; training |
| Model performs worse at a new hospital |  | Hold out one hospital for external validation; recalibrate per site |
| Ethics/data-sharing delays |  | Start approvals in month 0; federated learning option |

## §7 Preliminary data (the biggest factor for NIH, Wellcome and R33)

| Item | Status / result |
| --- | --- |
| Number of images already collected | ______ |
| Pilot model performance (sensitivity / specificity / AUC) | ______ |
| Publications/abstracts by team on oral cancer or AI | ______ |
| Prior grants on related work | ______ |
| Figures available (ROC curve, example heatmaps, app screenshots) | ______ |

## §8 Timeline / Gantt (by quarter)

| Activity | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ethics, data agreements, hiring | ■ |  |  |  |  |  |  |  |
| Image protocol & site training | ■ | ■ |  |  |  |  |  |  |
| Data collection & labelling |  | ■ | ■ | ■ | ■ |  |  |  |
| Model development |  |  | ■ | ■ | ■ |  |  |  |
| External validation |  |  |  |  | ■ | ■ |  |  |
| Prospective pilot |  |  |  |  |  | ■ | ■ |  |
| Analysis, publication, dissemination |  |  |  |  |  |  | ■ | ■ |

Milestones (deliverables with dates):

1. M__: ____

2. M__: ____

## §9 Master budget (build once, then map to each funder's categories)

| Item | Unit cost | Qty | Year 1 | Year 2 | Year 3 | Total | Site |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Personnel: research coordinator |  |  |  |  |  |  |  |
| Personnel: AI engineer / data scientist |  |  |  |  |  |  |  |
| Personnel: research nurses / dental assistants (×4 sites) |  |  |  |  |  |  |  |
| Personnel: annotator / pathologist time |  |  |  |  |  |  |  |
| Investigator effort/honoraria (where funder allows) |  |  |  |  |  |  |  |
| Equipment: smartphones/intraoral cameras (×4 sites) |  |  |  |  |  |  |  |
| Equipment: GPU workstation / server |  |  |  |  |  |  |  |
| Cloud compute & storage |  |  |  |  |  |  |  |
| Supplies: biopsy & histopathology costs |  |  |  |  |  |  |  |
| Participant reimbursement (travel, time) |  |  |  |  |  |  |  |
| Software licences / app development |  |  |  |  |  |  |  |
| Travel between sites |  |  |  |  |  |  |  |
| Training workshops for screeners |  |  |  |  |  |  |  |
| Conferences / publication (open-access fees) |  |  |  |  |  |  |  |
| Ethics review fees |  |  |  |  |  |  |  |
| Indirect costs / overhead (funder's rate) |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |

Exchange rate used: 1 USD = ____ THB (state the date).

## §10 Ethics, data protection & regulation

| Item | Status | Ref no. / date |
| --- | --- | --- |
| Ethics approval – lead hospital | ☐ submitted ☐ approved |  |
| Ethics approval – partner 2 / 3 / 4 | ☐ ☐ ☐ |  |
| Consent forms (Thai + English), incl. consent to photograph and to use images for AI | ☐ |  |
| Thai PDPA compliance: data controller/processor roles, de-identification, DPO contact | ☐ |  |
| Data-sharing agreement among 4 hospitals | ☐ |  |
| Data storage location & security (on-premise / cloud in Thailand) | ☐ |  |
| Thai FDA (อย.) classification of AI as Software as a Medical Device, if aiming for clinical use | ☐ |  |
| Clinical trial registration (Thai Clinical Trials Registry / ClinicalTrials.gov) if prospective | ☐ |  |
| NIH: does the study meet NIH's clinical trial definition? (answer NIH's 4 questions) | ☐ yes ☐ no |  |

## §11 Outputs, outcomes, impact (Thai funders score this heavily)

| Level | Thai term | Your content |
| --- | --- | --- |
| Outputs (direct products) | ผลผลิต | e.g. annotated dataset of ____ images; AI model; screening app; ____ publications |
| Outcomes (changes in use) | ผลลัพธ์ | e.g. ____ screeners trained; app used at ____ sites; referral time reduced by ____ |
| Impact (long-term) | ผลกระทบ | e.g. more early-stage diagnoses; lower mortality and treatment cost; national screening policy |
| Users / beneficiaries | ผู้ใช้ประโยชน์ | ____ |
| Alignment with national plans | ความสอดคล้องกับแผน ววน. / OKR | ____ |
| Commercialisation / IP plan | ทรัพย์สินทางปัญญา | ____ |
| Sustainability after funding ends |  | ____ |

## §12 Letters of support (collect early; signed, on letterhead)

| From | Says what | Status |
| --- | --- | --- |
| Director of each partner hospital (×4) | Commitment of staff, space, patient access, data | ☐ ☐ ☐ ☐ |
| Head of pathology department | Histopathology confirmation | ☐ |
| AI/technical partner | Compute, engineering support | ☐ |
| Provincial health office / MOPH / NCI Thailand | Interest in adopting screening tool | ☐ |
| Foreign collaborator (for NIH/Wellcome/e-ASIA) | Specific role, effort | ☐ |

## §13 Standard attachments (keep PDFs ready)

☐ Institutional registration certificates

☐ Ethics approvals (×4)

☐ Signed data-sharing agreement

☐ CVs (EN & TH)

☐ Letters of support

☐ Facilities description for each site (clinics, imaging, labs, IT, compute)

☐ Bank account details of the lead institution

☐ Audited financial statement (some private funders ask for this)

☐ Logo / branding permissions (for publicity)